Digital Transition for accessible agrotourism

Action 101167990

D3.1 Train the Trainer Toolkit

Module 4: Business Model Canvas and learning methodologies

Agile Methodologies

Disclaimer

Funded by the European Union. Views and opinions expressed are however those of the author(s) only and do not necessarily reflect those of the European Union or European Innovation Council and SMEs Executive Agency (EISMEA). Neither the European Union nor the granting authority can be held responsible for them.

Table of Contents

1.	Introduction	4

2.	What is Agile	4

3.	Core Frameworks (Plain English)	4

4.	Benefits for a small agrotourism business	4

5.	Advantages and drawbacks	5

6.	Legal and accessibility notes	5

7.	Self-assessment checklist	5

8.	Implementation steps – Four-Week Pilot Sprint	6

9.	Trainer Toolbox	6

# Introduction

Agile is a family of project‑management practices that deliver small, workable pieces of value on a short, repeatable cycle. For a farm‑stay business, this could mean adding a secure payment step this week and an accessible room‑guide video next week—instead of waiting months for a full site rebuild. This guide gives trainers plain‑language content, a checklist and step‑by‑step plan so owners can try Agile without jargon or extra software costs.

# What is Agile

Agile is a lightweight way to plan, build and improve products or services. Work is sliced into small tasks, prioritised by business value and delivered in short cycles called **sprints** (usually 1‑4 weeks). Teams meet daily for a quick check‑in, show finished work at the end of each sprint and discuss what to improve next time.

# Core Frameworks (Plain English)

- Scrum – Fixed‑length sprints, one ‘Product Owner’ prioritises tasks, daily 15‑minute stand‑up, demo and retrospective at sprint end.

- Kanban – Work items flow through ‘To Do, In Progress, Done’ columns; limit how many tasks sit in progress at once; no fixed sprint length.

- Scrumban – Mix of both: sprint‑style planning with Kanban flow limits for ongoing tasks.

# Benefits for a small agrotourism business

- Quick wins: see improvements every 1‑2 weeks, not after a long project.

- Flexible: change priorities when guest needs or rules change.

- Greater transparency: everyone sees the board and knows progress.

- Lower risk: small tasks mean fewer surprises and easier fixes.

# Advantages and drawbacks

| Advantages | Drawbacks |
| --- | --- |
| Short feedback loops catch errors early. | Needs discipline to keep tasks small and focused. |
| Simple visual boards reduce meetings and emails. | Daily stand‑up can feel excessive for one‑person teams—may switch to twice per week. |
| Works with free tools like Trello or physical sticky notes. | Changing scope too often can exhaust the team without a clear definition of done. |

# Legal and accessibility notes

- If you use an online board (Trello, Jira Cloud), select EU‑based data storage to comply with GDPR.

- Set board colour themes with high contrast; ensure status labels are readable by colour‑blind users.

- Attach only necessary guest data to tasks; avoid posting personal emails or phone numbers in public team spaces.

- When recording sprint demos, add captions for remote participants.

# Self-assessment checklist

☐	Backlog list created and prioritised by business value.

☐	Sprint length chosen (1‑4 weeks) and shared with team.

☐	Task board visible to everyone (physical or digital).

☐	Each task small enough to finish in ≤ 1 week.

☐	Daily or twice‑weekly stand‑up scheduled and under 15 minutes.

☐	Definition of Done agreed (tested, accessible, documented).

☐	Sprint review and retrospective booked at end of cycle.

☐	Online tools use EU data region and have readable colour contrast.

☐	Only essential guest data stored on task cards.

Indicative time for the learning course: a half-day (3–4 h) intro (Agile basics + set up board + first sprint plan), or a four-week pilot with weekly 60-minute sessions (planning, check-in, review, retrospective).

# Implementation steps – Four-Week Pilot Sprint

- List all improvement ideas in one backlog document (spreadsheet or Trello).

- Rate each idea 1–5 for guest impact and effort, sort by highest impact, lowest effort.

- Choose a sprint length (two weeks works well for first attempt).

- Select 3–5 top backlog items that fit comfortably into the sprint; write each as a task starting with a verb, e.g., “Add alt text to 20 images”.

- Set up a simple Kanban board with columns: To Do, In Progress, Done; limit ‘In Progress’ to 3 tasks.

- Assign roles: one person acts as Sprint Lead (keeps timeboxes), everyone else contributes tasks.

- Hold a stand‑up every morning: each person says (1) what I did, (2) what I plan, (3) any blockers; time‑box to 15 minutes.

- At end of sprint, demo finished tasks to team or advisor; note guest feedback if any task was live on the website.

- Run a 30‑minute retrospective: What went well? What to improve? Add one process tweak to next sprint.

- Repeat for a second sprint, adjusting task size and board limits using lessons learned.

# Trainer Toolbox

- Trello Simple Scrum Board Template -

https://trello.com/templates/agile-scrum

- Kanban 101 Article (Atlassian) - https://www.atlassian.com/agile/kanban

- Free Retrospective Cards - https://retromat.org

- Google Sheets Backlog Template – Link to a clean sheet for rating impact vs effort.

- Sprint Timer App – Keeps daily stand‑ups and retrospectives on time.