Digital Transition for accessible agrotourism

Action 101167990

D3.1 Train the Trainer Toolkit

Module 8: Project planning and fundraising support

Support in project identification and proposal drafting

Disclaimer

Funded by the European Union. Views and opinions expressed are however those of the author(s) only and do not necessarily reflect those of the European Union or European Innovation Council and SMEs Executive Agency (EISMEA). Neither the European Union nor the granting authority can be held responsible for them.

- Table of Contents

1.	Introduction	4

2.	Quick map of financing options (context for “fit”)	4

3.	Where to look for opportunities (and how to read them fast)	5

4.	Go/No-Go - decision in 15 minutes	5

5.	Project identification canvas (one page)	5

6.	Proposal structure — write in plain language	6

7.	Work plan template (copy/paste)	7

8.	Budget template (categories to include)	8

9.	Evaluation criteria alignment	8

10.	Accessibility & GDPR — make it explicit (and fundable)	9

11.	Cashflow, loans, and de minimis — reduce risks	9

12.	Proposal sprint timeline (6–8 weeks)	9

13.	Common pitfalls (and how to avoid them)	10

14.	Reviewer’s lens - pre-submission checklist	10

15.	Documentation as the Foundation of Funding	10

16.	Basic document checklist (with explanations)	10

17.	Smart document review - how trainers can help (expanded)	11

# Introduction

Small agrotourism businesses often have creative ideas but limited budgets. External funding (grants, low-interest loans, co-financing, sponsorships) can unlock projects such as:

- booking systems hosted in the European Union,

- websites accessible to people with disabilities,

- audio guides for visitors using codes placed on signs,

- simple guest feedback systems.

The trainer’s role is to help transform local needs into projects that can be funded, keep the process simple, and ensure that proposals are compliant, accessible, and realistic.

This guide includes:

- A practical pathway from idea → identifying opportunities → quick eligibility check → drafting a proposal → submission.

- Checklists and templates for trainers to use with businesses.

- Built-in steps for accessibility (WCAG 2.2) and GDPR compliance, which are often evaluated positively by funders.

# Quick map of financing options (context for “fit”)

Use this overview to decide which type of funding best matches the project idea:

- Grants and subsidies: non-repayable but with strict rules. Best for digitalisation, accessibility, training, or green transition.

- Preferential loans: low-interest loans with grace periods; in some cases part of the loan can be forgiven. Good if cashflow is predictable.

- Crowdfunding, sponsorships, or vendor financing: combine marketing with funding or allow low upfront costs. Carry risks such as long-term contracts or unfulfilled promises.

Trainer tip: The best choice depends on the stage of the business, the risks it can take, available own contribution, and the purpose of the investment — not only on the idea of “free money.”

# Where to look for opportunities (and how to read them fast)

- Regional and national calls in tourism and digitalisation: published by government agencies or regional authorities. Always check calendars of upcoming calls.

- Local development groups: rural development or community-based initiatives often fund small-scale projects.

- Operators appointed by agencies: organisations contracted to manage funding programs; they often provide direct support to SMEs.

Why this matters: Rules differ depending on region, business size, or sector. Funding intensity and eligibility can change even within the same program. It is important to keep a simple pipeline and update it often.

# Go/No-Go - decision in 15 minutes

Before writing, confirm:

- The business is eligible (region, size, sector, timing).

- The funding covers the planned activities (digitalisation, accessibility, training).

- The business can manage pre-financing (grants often reimburse later, loans may require collateral).

- The outputs and timeline are realistic for a micro-business (usually up to 12 months).

- Accessibility and GDPR are included - this can improve evaluation.

Use a one-page checklist with the owner and identify any blockers immediately.

# Project identification canvas (one page)

Fill this with the SME to clarify the project idea:

- Problem/need (with evidence), for example, many guests abandon bookings online, staff spend time guiding guests to the property.

- Beneficiaries - families, cyclists, remote workers, people with low vision, reception staff.

- Solution: EU-hosted booking system, audio guides activated with simple codes, staff procedures.

- SMART objectives: e.g., reduce booking drop-offs by 15% in 6 months, reduce phone calls asking for directions by 30% in 3 months.

- Outputs: accessible website, videos with captions, documents with alternative text, audio route, written procedures.

- Impact: more direct bookings, inclusive access, saved staff time, higher guest satisfaction.

# Proposal structure — write in plain language

- Executive summary (1 page)

  - Short overview: problem, solution, budget, impact, and urgency.

  - Example: “30% of guests abandon mobile bookings. We will implement a booking system hosted in the EU that meets accessibility standards (WCAG 2.2). This will cost €20,000 and increase direct bookings by 15% within 6 months.”

- Context & needs

  - Local situation, seasonality, guest groups, and barriers (e.g., payment problems, lack of accessibility).

  - Use data: guest feedback, booking statistics, surveys.

- Objectives (SMART)

  - Specific, Measurable, Achievable, Relevant, Time-bound.

  - Example: “Launch accessible booking system by June; train 4 staff members; reduce calls asking for directions by 30% in 3 months.”

- Method / work Plan

  - Divide into phases (Setup, Accessibility, Booking System, Training).

  - Define roles and responsibilities.

  - Add timeline with milestones.

  - Include accessibility and GDPR actions in each phase.

- Budget & co-financing

  - Main categories: software, hardware, accessibility services, training, communication, contingency.

  - Show own contribution and attach supplier quotes.

  - Include accessibility costs (captions, alt text, audits) as eligible items.

- Risk & mitigation

  - Identify top 5 risks (e.g., delivery delays, staff turnover, cashflow gaps).

  - Provide countermeasures (alternative suppliers, extra training, bridge financing).

- Accessibility & GDPR

  - Ensure WCAG 2.2 standards (contrast, text alternatives, keyboard navigation).

  - Add privacy notice, confirm data stored in EU, define retention rules.

  - Plan audits before and after implementation.

- Monitoring & evaluation

  - Define KPIs (bookings, guest satisfaction, website visits).

  - Set baselines and targets.

  - Assign who measures and when (monthly by owner, quarterly by trainer).

- Sustainability

  - Explain continuation after funding: subscription renewals, staff training, yearly accessibility checks.

  - Show how revenues will cover future costs.

- Dissemination

  - How results will be shared: website, social media, local media, printed materials.

  - Ensure all materials are accessible (contrast, captions, plain language).

# Work plan template (copy/paste)

| Phase | Main tasks | Deliverables | Months | Responsible |
| --- | --- | --- | --- | --- |
| Setup | Procurement, vendor selection, hosting in EU, kick-off | Signed contracts, project plan | M1 | Owner |
| Accessibility Upgrade | Accessibility audit, fixes, captions, alternative text, accessible PDFs | Accessible website & documents | M1–M3 | Web lead |
| Booking System | Configuration, payments, mobile testing | Booking system live, test report | M2–M4 | IT/host |
| Audio Guidance | Script writing, recording, installation, trial | Audio route live, documentation | M3–M4 | Operations |
| Training & Handover | Staff training, step-by-step manuals, backup drill | Training logs, manuals | M4 | Trainer |

# Budget template (categories to include)

- Software (booking system, chatbot; 12 months)

- Accessibility services (captions, text alternatives, accessible PDFs)

- Hardware (signage codes, router, tablets)

- Training & mentoring (with captioned recordings)

- Implementation labour (timesheets)

- Communication (accessible brochures, translations)

- Contingency 10%

- Funding source (grant/own contribution)

# Evaluation criteria alignment

Match your text with typical funder evaluation criteria:

- Relevance & need - data-based problem, accessibility gaps (Executive summary, Context).

- Impact & innovation - measurable outcomes, inclusion (Objectives, Impact).

- Quality of method - realistic phases, GDPR and accessibility steps, risk plan (Work plan).

- Capacity & partnership — clear roles, letters of support (Team, Annexes).

- Value for money - unit costs, quotes, proof of co-financing (Budget).

# Accessibility & GDPR — make it explicit (and fundable)

- Budget for accessibility (WCAG 2.2 fixes, alt text, captions, accessible PDFs).

- GDPR compliance: lawful basis for each data field, EU data residency, consent records, retention schedule.

- Publish and update privacy notice.

- Keep evidence (screenshots, scans, meeting notes) in an EU-hosted cloud folder with clear names.

# Cashflow, loans, and de minimis — reduce risks

- Grants reimburse after delivery, show buffer or bridge financing.

- Preferential loans: check maximum amount, term, interest, and grace period, define eligible uses (equipment, software, implementation).

- De minimis aid: it is a tracked allowance, not direct cash, it reduces interest rate or fees.

- Loans require security (mortgage, guarantees, promissory notes).

# Proposal sprint timeline (6–8 weeks)

- Week 1: Go/No-Go, define team, fill Canvas, collect quotes.

- Week 2: Write Context & Objectives, gather evidence, draft Work Plan.

- Week 3: Draft Budget, request letters, write Accessibility & GDPR.

- Week 4: Full draft, internal review, fix gaps.

- Week 5: Finalise annexes, ensure accessible PDFs and captions.

- Week 6: Final checks, signatures, submit, prepare for questions.

- Weeks 7–8: Answer clarifications, prepare procurement.

# Common pitfalls (and how to avoid them)

- Using jargon → rewrite in plain language.

- Great idea but weak cashflow → add bridge plan or phase purchases.

- Treating accessibility as an afterthought → include it from the start.

- Eligibility mismatch → use the Go/No-Go checklist early.

- Late quotes or letters → request by Week 2.

# Reviewer’s lens - pre-submission checklist

- Executive summary covers problem, solution, budget, and impact.

- Objectives are SMART and linked to KPIs and budget lines.

- Work plan shows who does what and when, risks have solutions.

- Accessibility and GDPR are present in method, budget, outputs.

- All attachments are accessible (tagged PDFs, high contrast, captions).

- Budget totals match forms, co-financing is documented.

- The text aligns section by section with the evaluation criteria.

# Documentation as the Foundation of Funding

Funding is not only about the project idea. Every program requires formal evidence : company registration, tax certificates, financial statements, quotes, policies, and more. Many small businesses fail not because their ideas are weak, but because their documentation is incomplete, unclear, or submitted in the wrong format.

The trainer’s role is to:

- Help SMEs collect a standard pack of documents early, before any call is announced

- Teach them how to quickly identify the most important rules in regulations.

- Ensure proposals are supported by clear, consistent, and accessible evidence

# Basic document checklist (with explanations)

SMEs should always prepare these documents before applying:

- Company registration-license, national business number, or proof of legal status. Without this, most applications are automatically rejected.

- Tax clearance and social security certificates,  official confirmation that the business does not owe unpaid taxes or social contributions. These documents often have a short validity (30–90 days), so timing matters.

- Financial statements (last 12 months)-balance sheet or income statement. For micro-businesses, even a simplified cashflow is enough. Funders want to see financial stability.

- Project evidence supporting data such as guest satisfaction surveys, booking statistics, photos of the facility, or screenshots of website analytics. This shows that the problem is real, not imagined.

- Supplier quotes-at least two for each major purchase (e.g., website redesign, equipment). Funders use this to check market value and avoid overpricing.

- Staff list, names, roles, type of contract. Funders may require proof of staff capacity to deliver the project.

- Policies: privacy notice for handling guest data, accessibility statement for digital tools, safety certificates for facilities. These demonstrate compliance with legal standards.

- Previous funding history, record of past grants, subsidies, or de minimis aid. This is necessary to calculate remaining eligibility and ensure no double funding.

# Smart document review - how trainers can help (expanded)

Reading full program regulations can feel overwhelming for SMEs. Trainers should guide them to focus on the most critical parts first:

- Eligibility section

- Check if the business fits by region, company size, sector, and project type.

- Example: some calls exclude accommodation providers unless they are rural-based.

- Funding intensity

- Identify the share of project costs covered by the grant (e.g., 70%).

- Clarify what portion the SME must co-finance and whether in-kind contributions (staff time, own equipment) are acceptable.

- Eligible costs

- Carefully list which expenses can be funded (e.g., software licenses, training) and which cannot (e.g., land purchase, ongoing bills).

- Trainers should prepare a “yes/no” table with SMEs to avoid surprises later.

- Reporting rules

- Check what proof is required for payment: invoices, bank transfers, timesheets, photos.

- Highlight if payments are advance (before spending) or reimbursement (after spending).

- Durability period

- Many funders require projects to remain active for 1–3 years after completion.

- Example: if a guesthouse builds a new accessible website, it must stay online and functional during the durability period.

- Consequences of failure

- Regulations specify when funds must be repaid (e.g., selling equipment too early, not meeting KPIs).

- Trainers should underline these risks clearly to SMEs.

Practical trainer strategies:

- Use a highlighter exercise: SMEs mark the five key sections in the regulation document.

- Provide a summary sheet where they can rewrite complex rules in plain language.

- Encourage SMEs to ask themselves three questions for every rule:

- Does this apply to me?

- What evidence is needed?

- What happens if I miss it?