## Template
LOGO |  |  | Construction Schedule Template |  |  |  | overall progress | 3.846%
Done? | Stage | Task | Assigned To | Start Date | End Date | Duration (Days) | Status | Progress
| Pre-construction | Design and planning | John Smith | 2025-06-01 | 2025-06-14 | 13 | Done | 100%
| Pre-construction | Sample approval | Laura Walker | 2025-06-15 | 2025-06-28 | 13 | In Progress | 25%
| Pre-construction | Bidding | John Smith | 2025-06-29 | 2025-07-12 | 13 | In Progress | 10%
| Pre-construction | Contract execution | Laura Walker | 2025-07-13 | 2025-07-30 | 17 | In Progress | 12%
| Pre-construction | Obtain permits | John Smith | 2025-07-27 | 2025-08-30 | 34 | In Progress | 5%
| Pre-construction | Permits approved | Laura Walker | 2025-08-30 | 2025-09-02 | 3 | Not Started | 0%
| Construction | Mobilisation | John Smith | 2025-09-03 | 2025-09-06 | 3 | Not Started | 0%
| Site work | Rough grading | Laura Walker | 2025-09-07 | 2025-09-20 | 13 | Not Started | 0%
| Site work | Footings | John Smith | 2025-09-21 | 2025-09-23 | 2 | Not Started | 0%
| Site work | Foundation | Laura Walker | 2025-09-25 | 2025-10-18 | 23 | Not Started | 0%
| Site work | Inspection: Foundation | John Smith | 2025-10-19 | 2025-10-20 | 1 | Not Started | 0%
| Rough framing | Floors | John Smith | 2025-11-16 | 2025-11-29 | 13 | Not Started | 0%
| Rough framing | Walls | Laura Walker | 2025-11-30 | 2025-12-13 | 13 | Not Started | 0%
| Rough framing | Roof | John Smith | 2025-12-14 | 2025-12-27 | 13 | Not Started | 0%
| Rough framing | Structural repairs | Laura Walker | 2025-12-28 | 2026-01-10 | 13 | Not Started | 0%
| Rough framing | Inspection | John Smith | 2026-01-11 | 2026-01-24 | 13 | Not Started | 0%
| Exterior | Windows | John Smith | 2026-02-08 | 2026-02-21 | 13 | Not Started | 0%
| Exterior | Doors | Laura Walker | 2026-02-22 | 2026-03-07 | 13 | Not Started | 0%
| Exterior | Masonry & Roofing | John Smith | 2026-03-08 | 2026-03-21 | 13 | Not Started | 0%
| Exterior | Inspection | Laura Walker | 2026-03-22 | 2026-04-04 | 13 | Not Started | 0%
| MEP rough-in | HVAC | Laura Walker | 2026-04-19 | 2026-05-02 | 13 | Not Started | 0%
| MEP rough-in | Plumbing | John Smith | 2026-05-03 | 2026-05-16 | 13 | Not Started | 0%
| MEP rough-in | Electrical | Laura Walker | 2026-05-17 | 2026-05-30 | 13 | Not Started | 0%
| MEP rough-in | Inspection | John Smith | 2026-05-31 | 2026-06-13 | 13 | Not Started | 0%
| Interior | Insulation & Drywall | John Smith | 2026-06-28 | 2026-07-11 | 13 | Not Started | 0%
| Interior | Inspection | Laura Walker | 2026-07-12 | 2026-07-25 | 13 | Not Started | 0%