## Tool 7
The action plan is a planning tool aimed at implementing measures to improve the organization's capacity to mitigate the risk of gender-based violence and strengthen protection and safeguard mechanisms.
ACTION | PERSON RESPONSIBLE | RESOURCES NEEDED/AVAILABLE (e.g. finance, human resources, logistics) | EXPECTED COMPLETION DATE | STATUS
(not yet started/ongoing/completed)
Core Standard 1: organization-wide procedures
The organization has a procedure related to violence risk mitigation and safeguarding-related mechanisms that describes standards, other preventive, reporting, monitoring, investigation and corrective measures.
Example 1: Review human resource procedures to include definitions and standards of behavior | Anna | n/a | March 30, 2024 | Ongoing
Example 2: Revise the code of conduct to include specific aspects related to sexual exploitation | Bruno | n/a | March 30, 2024 | Ongoing
Example 3: xxx
Core Standard 2: Management and human resource systems of the organization
Management and human resources systems take into account violence risk mitigation and safeguarding mechanisms
Example 4: Foresee criminal record or other ongoing investigation of candidates checks | Anna | n/a | May 31, 2024 | Not yet started
Example 5: XXX
Core Standard 3: Mandatory training
The organization organizes mandatory training sessions for staff
Example 5: Develop a full-day in-person training package | Gina's role: identifying and recruiting a consultant. | Amount requested: € 1000 | May 31, 2023 | Not yet started
Example 6: Revise orientation package for new staff to include training requirement | Alfonso | n/a | April 30, 2023
Example 7: XXX
Fundamental Standard 4: Reporting
The organization has mechanisms and procedures for reporting allegations (or suspicions) of gender-based violence, abuse, and exploitation committed by its staff
Example 8: Design, translate and widely disseminate posters on awareness and reporting mechanisms in all workplaces | Paul | Amount requested: €1500 (translation, graphics, printing) | May 1, 2025 | Not yet started
Available: €300 (translation)
Core Standard 5: Support and referral to support services.
The organization has a system in place to ensure that survivors of gender-based violence, including children , receive immediate professional support by referring them to the appropriate services.

## Tool 11
Mapping formal and informal resources and services in the area can be guided by the following questions: Who are the community stakeholders with whom the CSOs already have active relations that could be involved in planning? Who are the people already active in the area who are involved in hospitality and/or have activities relevant to this program? Who are the stakeholders already active in the area providing specialized support to people at risk or survivors of gender-based violence? What services do they offer? Who are the stakeholders who already have ongoing activities to facilitate the integration of hosted families in the territory in line with the specific needs of all its members? Who are the community stakeholders with whom the organization can activate new connections in order to involve them in planning? How can individuals be contacted directly? Is there a list of contact persons from associations, organizations, formal and informal groups? How can individuals take part in the activities? Has it been defined what role, responsibilities, and functions they may have? Can a formal collaborative agreement be structured with those to be involved? What, if any, critical issues need to be managed in network involvement? And/or what barriers exist (language, cost or transportation, or other criteria and modalities to regulate access to their services and activities)?
NETWORK RESOURCES
Name of organization | Main activities | Opening hours | Cultural mediation available | Cost and transportation | Contact person
Material assistance and basic necessities
Economic area and access to employment
Education and training area
Health, including sexual and reproductive health, and mental health
Early childhood care
Housing
Legal Area
Protection services (including anti-violence centers and anti-trafficking services)
Integration and leisure area